## Slide 1: Mapper for Android
Twin Cities Edition
IE 5541: Project Presentation
Andrey Bruslavtsev Ian De Silva Jared Swanson Jonathan Lee
Kristin Dahl Sriram Rajendran Usha Kumar Weston Platter
April 23, 2012
Notes: Kristin

## Slide 2: Overview
The Minneapolis Skyway System and U of M “Gopher Way” can be difficult to navigate.
There are apps for iOS to help navigate the Skyway.
What about Android?
Notes: Kristin

## Slide 3: Project Objective
Video
Notes: Kristin

## Slide 4: Deliverables
Notes: Jon

## Slide 5: Product Deliverables
Installable Android Application
Marketing & Distribution Materials
Notes: Jon

## Slide 6: Major Functionalities
Map of Minneapolis Skyway
Map of U of M tunnel system
Search
Search History
Routing
Save Favorites
Help
Notes: Jon

## Slide 7: Map of Skyway/Tunnel System
Our app draws the skyway/tunnel system as a map overlay.
How?
  Open source libraries and Android API
  Google Maps: Provided map images
  Google Earth: Tool to extract coordinate data
Notes: Jon

## Slide 8: Search & Route
Our app allows users to search for nearby businesses
Yelp API - used to provide business data
Routing
  Draw shortest path to destination based on current location
  Location is updated via device’s native positioning system
Notes: Jon

## Slide 9: Favorites
Our app allows users to save a business as for quick access
Notes: Jon

## Slide 10: Marketing
Minnesota Daily
  Contacted publishers
  Interested – want to see additional functionality
Flyers created for campus and downtown Minneapolis
Facebook page
Android Marketplace
  Appeal to general public
Notes: Andrey

## Slide 11
Notes: Andrey

## Slide 12
Notes: Andrey

## Slide 13: Project Approach
X
Notes: Jared

## Slide 14: Project Approach
Plan
Process
Risk Analysis
Notes: Jared

## Slide 15: Plan: Baseline
Project Mgt.
Deployment & Future Work
Software
Development
Team Prep Work
Notes: Jared

## Slide 16: Plan: Current
Project Mgt.
Deployment & Future Work
Software
Development
Team Prep Work
Notes: Jared

## Slide 17: Approach: Processes
Diagram from S. McConnell, “Right-Sizing Agile Development,” 01-Oct-2008.
Notes: Weston – What do you think our profile is?

## Slide 18: Process: SCRUM
2 week Sprint
(Iteration)
Scrum Meeting
Req. 2
Req. 1
Req. 3
Sprint Backlog
Shippable
Product
(Prototype)
Product Backlog
Contains Stories
Contains Tasks
Sprint Planning Meeting (Kick-off)
Sprint
Wrap-up
Meeting
Notes: Ian
- Product Backlog created from WBS in git.
Iteration planning meeting held to determine scope for iteration (Sprint)
Scrum meeting held weekly with an e-mail “scrum” on Wednesdays (lasted ¾ of the semester)
Sprint Wrap-up: Reflected on last iteration and tried to correct. We merged with planning.

## Slide 19: Problems: Process Breakdown
Varying acceptance of process
Time constraints toward end of semester
Resistance to testing in favor of increased functionality
Ineffective communication
Image from:
http://atozautocar.com/car-how-to/3540/solve-overheating-car.jsp
Notes: Ian
Talk to: We had lots of communication, it was just ineffective.
1) Agreed understanding of the situation, claim responsibility for follow-up.
11) Understood tasks, but did not understand integration.
What was lacking:
Integration tie-in points

## Slide 20: Problems: Process Breakdown
Notes: Ian
Talk to: We had lots of communication, it was just ineffective.
1) Agreed understanding of the situation, claim responsibility for follow-up.
11) Understood tasks, but did not understand integration.
What was lacking:
Integration tie-in points

## Slide 21: Problems: Ineffective Communication
<Picture>
Lack of time
Size of team
Notes: Weston:
Lack of time
Size of team

## Slide 22: Failed Communication
Team
Technical Work
Marketing
Software Development
Failed to integrate
Notes: Weston

## Slide 23: Risk Analysis
Risk – mitigation strategy
Code quality of application – testing
Complexity of project scope – reduce scope
Licensing issues with employers – release
Image from: http://cache.virtualtourist.com/15/4933424-Supja_Stina_tightrope_walking_Sveta_Nedjelja.jpg
Notes: Weston

## Slide 24: Lessons Learned
Notes: Usha

## Slide 25: Lessons Learned
Execution
  Well-defined processes , helped us to be dynamic
  Clear task identification
  Good development & co-ordination tools
  Timely identification of risk
Team Dynamics
  Weekly Team meetings
  Motivated & responsible team
Technical
  Learned about Android programming
  Learned about team dynamics
What Worked
Notes: Usha

## Slide 26: Lessons Learned
Execution
  Communication plan
  Virtual SCRUM
  Meeting documentation
  Quality was compromised for functionality
  No at-a-glance way of tracking
Technical
  Coordination tools
  Learning curve
What Didn’t
Notes: Usha -- Are you going to talk on what we’d do differently next time?

## Slide 27: Lessons Learned
Execution
  Close monitoring of task progress
  Active use of task tracker, for better utilization of resources.
Team Dynamics
  Daily tele scrum
  Forum to discuss issues and sharing ideas.
Technical
  Knowledge sharing sessions
  visual configuration management tool
What could have been done
Notes: Usha

## Slide 28: Future?
Aesthetics
Skyway closures
Indicate floor changes
<More?>
Notes: Sri

## Slide 29
Questions?
Notes: Sri